## Test Report
TEST REPORT TEMPLATE - PROJECT OVERVIEW
Project overview
Project basic information
Project Name | Fahasa Online Ordering System
Product Name & Version | Fahasa Web v1.2
Product Description
Project Description | E-commerce platform for book purchasing
| Project Description - Mission | Ensure system quality before release
| Project Description - Output Product | Stable and bug-free release
| Project Type | Web Application
Project Duration | Start Date | 2026-03-01 | End Date | 2026-03-30
Test Cycle |  | Test Execution Status
Metric | Count | Status | Count
PASSED | 85 | EXECUTED | 100
FAILED | 15 | PENDING | 10
Total Tests Executed | 100 | IN PROGRESS | 5
|  | BLOCKED | 5
|  | SUB-TOTAL (TEST PLANNED) | 120
|  | TOTAL | 120

## Details
Functions | Description | Percentage of test cases executed | Percentage of test cases passed | Test cases pending | Priority | Remarks
Login | User login with valid/invalid credentials | 90% | 85% | 2 | High | Minor UI issue
Search | Search books by keyword | 100% | 95% | 0 | Medium
Checkout | Place order and payment | 80% | 70% | 5 | Critical | Payment bug found

## Defects
DEFECT SUMMARY
Severity | Count
Critical | 2
High | 5
Medium | 6
Low | 4
Total Defects | 17

## Environment
TEST ENVIRONMENT
Hardware | Intel i7, 16GB RAM
Software | Chrome, Postman
Operating System | Windows 11
Browser | Google Chrome v120

## Risks & Issues
RISKS & ISSUES
ID | Description | Impact | Mitigation
R1 | Payment gateway unstable | High | Retry mechanism
R2 | Server downtime | Critical | Backup server